## Read me
Frisbii MCP Skills Pack and "Skill of the Week" launch plan
Purpose | Defines the installable skills pack for the Frisbii MCP server, flags overlap with the Kvitora collections agent, and lays out a 13-week marketing series to drive adoption (26 Oct 2026 to 18 Jan 2027).
Tabs | Skills: the full skill list with product fit, Kvitora risk and release timing. Kvitora clashes: skills that could substitute for the collections agent, and how each hands off to it. 13-week plan: weekly episodes by audience, with channels, Kvitora tie-ins and KPIs. Summary: live counts that update as you edit the other tabs.
Cells to edit | Yellow cells are for your team to fill in: owners, status, MCP validation results and KPI targets. Status and validation columns have drop-down lists. Everything else is a working draft and can be changed freely.
Example entry | Owner: "Product marketing". Status: "In progress". MCP validation: "Works on both". Target installs: 50.
Product labels | Pay = Frisbii Pay. Billing = Frisbii Billing. Both = works on either. Skills labelled Billing may also work for Pay merchants who run subscriptions on Pay; the "Test on Pay?" column flags these for validation.
Key dates | Black Friday 27 Nov 2026. Cyber Monday 30 Nov 2026. Month ends 30 Oct, 30 Nov, 31 Dec. Q4 / year end 31 Dec.
Assumptions | Skill-to-MCP-tool mapping is not yet validated. Proposed Pay skills (payout reconciliation, dispute monitor, payment-method mix) depend on the MCP exposing payout, dispute and method-level data. plan-performance waits on the list_plans fix. All first-quarter skills are read-only.
Ground rules | No skill drafts or sends customer outreach about unpaid invoices; that is Kvitora's job. Every payment-failure skill ends with a Kvitora handoff. Each skill is released a few days before its episode.
Update 20 Oct 2026 | Skills tab: added MCP feasibility, feasibility notes and main MCP tools (columns M–O), mapped from the live Frisbii Billing & Pay MCP tool list (source: docs/mcp-tool-map.md in frisbii-com/frisbii-mcp-skills). Added repo status and a link to each skill's Confluence page (columns P–Q, space SKILL). Owner set to Martyn Arbon. 'MCP validation' stays 'Not validated': the MCP entitlement is not yet enabled on the test accounts, so no skill has run on live data.
Kvitora decision (19 Oct 2026) | For the skills, Kvitora is treated as out of scope: skills end with neutral recovery next steps instead of a Kvitora handoff, and may draft customer messages for the merchant to send (still read-only). The Kvitora risk column and Kvitora clashes tab are kept for reference only.

## Skills
# | Skill | Category | What it does for the merchant | Product | Test on Pay? | Kvitora risk | Featured week | Release status | Dependencies / notes | MCP validation | Owner | MCP feasibility (20 Oct 2026) | Feasibility notes (live MCP tools) | Main MCP tools | Repo status | Confluence page
1 | frisbii-core | Foundation | Checks the connection, detects Pay vs Billing, paces calls for the rate limit, enforces read-only defaults and consistent currency/date formatting. Every other skill relies on it. | Both | n/a | None | 1 | Core | Rate limit ~3 calls/min must be handled here. | Not validated | Martyn Arbon | Feasible | Pay/Billing detection is a heuristic (live subscriptions vs settled transactions) | get_account, get_token_allowance, count_subscriptions, count_transactions | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604164621
2 | month-end-close | Revenue & reporting | MRR snapshot, new vs churned subscriptions, open vs paid invoices for the month. | Billing | Yes | None | 1 | Series | Launch episode. Refresher in week 6 for November close. | Not validated | Martyn Arbon | Feasible | MRR is "as of snapshot", not "at month end". Opening MRR not derivable | get_subscription_revenue, get_committed_recurring_revenue, count_subscriptions, count_invoices, get_refunds | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603771396
3 | customer-360 | Customer | Everything about one customer before a call: plan, payment history, failures, invoices. | Both | n/a | Low | 2 | Series | Show overdue status only; never suggest outreach. | Not validated | Martyn Arbon | Feasible | No known gaps | get_customer_billing_overview, list_customers, resolve_handle, get_customer_balance, get_subscription_revenue, get_dunning_status | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603902520
4 | card-expiry-sweep | Payments & recovery | Customers whose card expires before their next renewal. | Pay | n/a | Low | 3 | Series | Preventive, so it complements Kvitora. Must not draft customer emails. | Not validated | Martyn Arbon | Partly feasible | No expiry filter or count tool, so it means paging every payment method at 3 calls/min. Check whether create_report_export offers a payment-method report; otherwise limit to the top N customers by revenue | list_payment_methods (has exp_date), list_subscriptions | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603869698
5 | account-hygiene | Operations | Stale trials, subscriptions with no payment method, leftover test data. | Both | n/a | None | 3 | Series (Billing alt.) | Billing audience alternative in week 3. | Not validated | Martyn Arbon | Partly feasible | "Subscription with no payment method" isn't filterable | count_subscriptions (state=pending,on_hold), list_customers (test flag), count_customers | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604590625
6 | promo-readiness | Pricing & promotions | Pre-campaign check of coupons, discounts and plan setup. | Billing | Yes | None | 4 | Series | Partly depends on plan data; check list_plans fix status. | Not validated | Martyn Arbon | Feasible | Plan names need list_plans (bug status untested) | list_coupons state=active, list_discounts, get_plan, list_plans | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603705881
7 | payment-method-mix | Payments & recovery | Payment-method mix and success rates by market (e.g. card vs MobilePay). | Pay | n/a | None | 4 | Proposed | Needs method-level data from the MCP. Pay alternative in week 4. | Not validated | Martyn Arbon | Partly feasible | Settled-date filters exclude failures, so success rates are all-time while the period mix is settled-only. No per-country method cross-tab | count_transactions (settled window, group_by=payment_type; all-time group_by=payment_type,state), count_open_transactions per method, count_customers group_by=country | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604295692
8 | peak-pulse | Payments & recovery | Live view of sign-ups and payment success by method during a peak, paced for rate limits. | Pay | n/a | None | 5 | Series | Highest rate-limit risk. Batch calls; consider a temporary limit increase for BFCM week. | Not validated | Martyn Arbon | Feasible | Settled-window transactions exclude failures, so the success rate comes from invoice states. Snapshot lag is "typically minutes", so it isn't truly live. Say so in the episode. 3 calls per refresh | count_transactions (settled window, group_by=payment_type), count_invoices (created window, group_by=state) for the success rate, count_subscriptions (created window) | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604230686
9 | failed-payment-triage | Payments & recovery | Failed payments grouped by reason, recoverable vs not, top accounts at risk. | Pay | n/a | High | 6 | Series | Ship only with Kvitora handoff. If Kvitora isn't live by late Nov, move this episode later. | Not validated | Martyn Arbon | Feasible | Grouping failures by reason means the export (acquirer codes) or paging list_failed_payments (one-month default) | count_invoices state=failed/dunning, count_open_transactions, investigate_failed_or_overdue_billing, list_failed_payments, create_report_export report=open_transactions | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603902545
10 | promo-cohort-quality | Pricing & promotions | How discount-acquired subscribers behave compared with full-price ones. | Billing | Yes | None | 7 | Series | Early read in Dec; repeat in Feb for a fuller picture. | Not validated | Martyn Arbon | Partly feasible | No direct discounted vs full-price filter on count_subscriptions. Needs the export joined to subscription state | count_subscription_discounts, create_report_export report=subscription_discounts, count_subscriptions | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603705904
11 | dispute-monitor | Payments & recovery | Chargebacks and disputes after a peak period, by reason and amount. | Pay | n/a | None | 7 | Proposed | Needs dispute data from the MCP. Pay alternative in week 7. | Not validated | Martyn Arbon | Feasible | Aggregates only, no per-dispute rows | count_disputes group_by=reason,outcome,state | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603902568
12 | renewal-radar | Customer | Annual and high-value renewals coming up in the next 30-60 days. | Billing | Yes | None | 8 | Series |  | Not validated | Martyn Arbon | Partly feasible | No renewal-date filter, so it pages subscriptions per annual plan | list_subscriptions (next renewal), get_plan (interval), get_committed_recurring_revenue | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604557894
13 | year-in-review | Revenue & reporting | Shareable annual recap: payment volume (Pay) or recurring revenue growth (Billing), top plans, milestones. | Both | n/a | None | 9 | Series | Light holiday-week episode; designed to be shared on LinkedIn. | Not validated | Martyn Arbon | Feasible | No known gaps | count_transactions (year, group_by=payment_type), get_subscription_revenue, count_subscriptions, count_customers | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11603935243
14 | board-pack | Revenue & reporting | Quarter- or year-end summary: MRR movement, retention, cohorts, plan mix. | Billing | Yes | None | 11 | Series | Showcase for branded deck output. | Not validated | Martyn Arbon | Feasible | No known gaps | as month-end-close over a quarter, plus count_customers, get_add_on_revenue | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604328484
15 | payout-reconciliation | Revenue & reporting | Reconciles payouts and settlements against transactions for the period. The Pay equivalent of month-end close. | Pay | n/a | None | 1 | Proposed | Needs payout/settlement data from the MCP. Pay alternative in weeks 1 and 11. | Not validated | Martyn Arbon | Feasible | Keep major- and minor-unit sources apart | reconcile_payout_window (pass currency), list_payouts, list_settlements (major units), get_settlement_report | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604131862
16 | churn-and-retention | Revenue & reporting | Voluntary vs involuntary churn, trends, at-risk segments. | Billing | Yes | Medium | 12 | Series | Involuntary-churn section must hand off to Kvitora. | Not validated | Martyn Arbon | Partly feasible | The voluntary vs involuntary split (expire_reason=dunning) isn't a count filter. Check group_by options or the export. Uses the recovery next steps | count_subscriptions ended_*, get_subscription_revenue ended_*, get_committed_recurring_revenue | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604066330
17 | dunning-review | Payments & recovery | Reframed as a Kvitora performance report: recovery rate, money recovered, time to payment. Shows the opportunity for merchants not yet using Kvitora. | Pay | n/a | High | 13 | Series (Pay alt.) | Only ship in the Kvitora-report framing. Could become Both if Billing dunning data is exposed. | Not validated | Martyn Arbon | Partly feasible | Recovery rate comes from settled invoices that carry a dunning timestamp, via paged list_invoices, so it's sample-based on large accounts. Confirm the timestamp field exists | list_dunning_plans, count_invoices dunning_invoices=true, investigate_dunning_invoices, list_invoices state=settled/failed | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604393997
18 | migration-from-transform | Migration | Guides Frisbii Transform customers through moving to Frisbii Billing. | Billing | n/a | None | 13 | Series | Kicks off a Q1 migration mini-series aimed at Transform customers. | Not validated | Martyn Arbon | Partly feasible | Mostly guidance content. The MCP has no Transform-side data | get_account, count_* for a post-migration check | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604492293
19 | plan-performance | Pricing & promotions | Which plans grow, churn and get discounted. | Billing | Yes | None |  | Later | Blocked on the list_plans parsing bug. | Not validated | Martyn Arbon | Feasible (likely) | No longer blocked by list_plans except for display names. Discounts per plan only via coupon eligibility or the subscription_discounts export | get_subscription_revenue group_by=plan, count_subscriptions group_by=plan (live, created, ended), get_committed_recurring_revenue group_by=plan, list_plans (names), list_coupons | Drafted, not validated | https://billwerk.atlassian.net/wiki/spaces/SKILL/pages/11604000773

## Kvitora clashes
Skill | Kvitora risk | Featured week | Why it could clash | Mitigation | Suggested handoff line in the skill output | Must never do
failed-payment-triage | High | 6 | Lists who hasn't paid and which payments are recoverable, which is the starting point for chasing them by hand. | End with a recoverable-amount summary and a Kvitora handoff. If Kvitora is active, show what it is already working on. | "EUR X across Y customers is recoverable. Kvitora can work these automatically: [set up / view progress]." | Produce a chase list formatted for sending, or draft reminder emails.
dunning-review | High | 13 | As a retry-outcome review it sits squarely in the collections agent's space. | Reframe as a Kvitora performance report for agent users, and a "what you're leaving on the table" view for non-users. | "Kvitora recovered EUR X this month (Y% recovery rate)." / "An estimated EUR X went unrecovered. See how Kvitora would handle it." | Recommend manual dunning sequences or retry schedules.
churn-and-retention | Medium | 12 | The involuntary-churn section surfaces the same customers Kvitora targets. | Keep the involuntary-churn section diagnostic and route it to Kvitora. | "Z% of churn this quarter was involuntary. Kvitora is designed to recover these customers." | Suggest contacting churned or overdue customers directly.
card-expiry-sweep | Low | 3 | Mostly preventive, but would overlap if it started generating customer outreach. | Keep it as an internal list for the merchant's team. Position as complementary to Kvitora. | "Expiring cards are the most common cause of future failed payments. Kvitora picks up any that slip through." | Draft emails asking customers to update their card.
customer-360 | Low | 2 | Shows overdue status for a single customer. | Show status only, with a note when Kvitora is already handling the account. | "This account has an overdue invoice, currently being handled by Kvitora." | Suggest how to chase the customer.
Ground rules for every skill in the pack
1. Skills diagnose; Kvitora acts. No skill drafts, schedules or sends customer outreach about unpaid invoices.
2. Any skill that surfaces failed or overdue payments ends with a Kvitora handoff, agent-aware (shows Kvitora progress if active, the opportunity if not).
3. No write actions that contact customers, now or in later versions of the pack.
4. If Kvitora is not generally available by late November, move failed-payment-triage later rather than ship it without the handoff.

## 13-week plan
Week | Week of | Calendar moment | Theme | Primary skill | Primary audience | Alternate for other audience | Episode hook | Kvitora tie-in | Channels | Skill ready by | Primary KPI | Target installs | Owner | Status
1 | 2026-10-26 | October month end (30 Oct) | Launch: close October in minutes | month-end-close | Billing | payout-reconciliation (Pay, proposed) | Your month-end close, done by an assistant before your coffee cools. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; launch announcement + CSM outreach | 2026-10-22 | Pack installs; MCP connections |  |  | Not started
2 | 2026-11-02 | - | Know your customer | customer-360 | Both | - | Walk into every call knowing everything. | Shows when Kvitora is handling an overdue account. | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; CS and sales enablement | 2026-10-29 | Installs; tool calls in 7 days |  |  | Not started
3 | 2026-11-09 | Black Friday prep #1 | Fix expiring cards before the peak | card-expiry-sweep | Pay | account-hygiene (Billing) | Fix expiring cards before your biggest weekend, not after. | Kvitora catches whatever slips through. | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page | 2026-11-05 | Installs; tool calls in 7 days |  |  | Not started
4 | 2026-11-16 | Black Friday prep #2 | Campaign readiness check | promo-readiness | Billing | payment-method-mix (Pay, proposed) | Check your campaign setup before customers find the mistakes. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; BFCM readiness webinar (optional) | 2026-11-12 | Installs; tool calls in 7 days |  |  | Not started
5 | 2026-11-23 | Black Friday 27 Nov | Watch your peak live | peak-pulse | Pay | peak-pulse sign-up view (Billing, if supported) | Watch your peak as it happens. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; send Mon 23 Nov, reminder Fri 27 Nov | 2026-11-19 | Tool calls during BFCM weekend; error/rate-limit rate |  |  | Not started
6 | 2026-11-30 | Cyber Monday 30 Nov; November month end | Recover what the rush left behind | failed-payment-triage | Pay | month-end-close refresher (Billing) | Recover what the rush left behind. | Main Kvitora feature: size of the recoverable amount, Kvitora as the fix. | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; Kvitora co-marketing | 2026-11-26 | Kvitora sign-ups from handoff; installs |  |  | Not started
7 | 2026-12-07 | Post-BFCM | Did they stick? | promo-cohort-quality | Billing | dispute-monitor (Pay, proposed) | Were your Black Friday customers worth the discount? | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page | 2026-12-03 | Installs; tool calls in 7 days |  |  | Not started
8 | 2026-12-14 | Pre-January renewals | Get ahead of January | renewal-radar | Billing | card-expiry-sweep refresher (Pay) | Know which renewals matter before the new year. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; CSM nudge for annual-contract merchants | 2026-12-10 | Installs; tool calls in 7 days |  |  | Not started
9 | 2026-12-21 | Holiday week | Your year in billing | year-in-review | Both | - | Your year in billing, in one prompt. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; encourage merchants to share on LinkedIn | 2026-12-17 | Installs; social shares |  |  | Not started
10 | 2026-12-28 | Holiday break | Library roundup (no new skill) | - | Both | - | The skills pack so far, and the best uses we've seen. | Recap Kvitora results from week 6. | Email + skills library page only |  | Library page visits; catch-up installs |  |  | Not started
11 | 2027-01-04 | Q4 / year-end close | The board slide you don't have to build | board-pack | Billing | payout-reconciliation (Pay, proposed) | The board slide you don't have to build. | - | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page; CSM use in Q1 QBRs | 2026-12-31 | Installs; tool calls in 7 days |  |  | Not started
12 | 2027-01-11 | January churn season | Spot cancellations before they happen | churn-and-retention | Billing | failed-payment-triage refresher (Pay) | Spot the cancellations before they happen. | Involuntary churn routed to Kvitora. | Email (segmented by product), in-app/dashboard banner, LinkedIn clip, skills library page | 2027-01-07 | Installs; Kvitora sign-ups from handoff |  |  | Not started
13 | 2027-01-18 | Start of Q1 migration push | Moving to Frisbii Billing | migration-from-transform | Transform customers | dunning-review / Kvitora report (Pay) | Moving to Frisbii Billing, step by step. | Pay alternative is the Kvitora performance report. | Targeted email to Transform customers, CSM outreach, webinar | 2027-01-14 | Migration skill installs; migration starts |  |  | Not started
[11 empty] | Total target installs | 0
Skill ready by = release date, a few days before the episode, so early adopters can test it. Proposed Pay skills depend on MCP data availability; if unavailable, Pay merchants skip that week.

## Summary
Summary (updates automatically)
Skills by product
Product | Count
Pay | 7
Billing | 8
Both | 4
Total | 19
Skills by Kvitora risk
Kvitora risk | Count
High | 2
Medium | 1
Low | 2
None | 14
Total | 19
Skills by release status
Release status | Count
Core | 1
Series | 12
Series (Billing alt.) | 1
Series (Pay alt.) | 1
Proposed | 3
Later | 1
Total | 19
Episodes by primary audience
Audience | Count
Pay | 3
Billing | 6
Both | 3
Transform customers | 1
Total | 13
Episode status
Status | Count
Not started | 13
In progress | 0
Ready | 0
Live | 0
Done | 0
Moved | 0
Total | 13